## README
Implementation Tracker Workbook
What is this workbook? | Workbook settings (edit the value column only)
A macro-free tracker that applies the R1 implementation operating model (implementation-operating-system) to day-to-day project work. It is a reference implementation of R1, not a separate method. | setting_key | value | editable | description
The bundled rows are synthetic data: three synthetic projects from R1 (Synthetic Projects A, B, and C). They are an illustrative example of the model in use, not customer data and not a record of historical use. | workbook_id | WBK-000001 | no | Workbook ID (WBK). Keep it when you copy the workbook for a new team.
What does R1 own? | workbook_version | 0.1.0 | no | R3 workbook version.
The lifecycle and phase statuses, gate outcomes, project, task, request, handoff, risk, and issue statuses, request transitions, severity definitions, the risk formula, readiness categories and weights, SLA and lead-time parameters, and the event catalog. | r1_repo | implementation-operating-system | no | The R1 repository this workbook implements.
What does R3 (this workbook) own? | r1_source_commit | 9acd25a4673facf2b3cca2467142987548949ce3 | no | The pinned R1 commit. Changes only through tools/sync_r1_contracts.py and a rebuild.
Workbook structure, the formulas that implement R1 rules, check columns, imports and exports, workbook metadata, and the Capacity Inputs export format. | shared_standard_version | 1.0.0 | no | Shared standard version pinned through R1.
Which R1 version is pinned? | calculation_as_of_at | 2026-10-05T23:59:59Z | yes | Evaluation time (ISO 8601 UTC, ending in Z) for due states and escalation states. A user-configurable parameter. No formula reads the clock.
R1 commit 9acd25a4673facf2b3cca2467142987548949ce3 (repository version 0.1.0), shared standard 1.0.0. See standard/standard-reference.yaml. | event_reconciliation_from_at | 2026-09-01T00:00:00Z | yes | Material changes at or after this time need an Event Log row. A user-configurable parameter.
What organization stage is selected? | selected_org_stage | startup | yes | Organization stage from R1 (startup, early_scale, structured_growth, mature). See config/stage-requirements.yaml.
The value selected_org_stage in the settings table. It sets which fields and controls config/stage-requirements.yaml treats as required, recommended, or optional. It never changes IDs, the event contract, readiness categories, or human gate authority. | operating_mode | starter | yes | starter or full. Same workbook, same model; Starter Mode only reduces what you update each week.
What is calculation_as_of_at? | generated_at | 2026-10-06T23:21:51Z | no | When this file was generated (the pinned R1 synchronization time, so builds are reproducible).
The evaluation time for every due-state and escalation formula, in ISO 8601 UTC (for example 2026-10-05T23:59:59Z). It is a user-configurable parameter. No formula reads the computer clock, so the same inputs always give the same results.
How do I use Starter Mode?
Set operating_mode to starter. Each week update Projects, Tasks, Risks and Issues, and Requests and Handoffs; review Readiness when a launch approaches; add Event Log rows only for material changes; then read KPI Summary. See docs/starter-mode.md.
How do I use Full Mode?
Set operating_mode to full. Use all 12 tabs: complete gate evidence, capacity exports, and full event reconciliation. Same workbook, same IDs, same R1 rules. See docs/workbook-guide.md.
Which cells do I edit?
White cells with dark blue headers: record fields on the record tabs, and the value column of the settings table below. Use the drop-down lists; they come from R1.
Which cells contain formulas?
Grey cells with grey headers. They reproduce R1 rules or check your records. Do not type over them. Green-headed tables are read-only mirrors of R1 configuration.
How do I export data?
Run python tools/build_workbook.py --exports, or save each table as CSV using the column list in config/export-map.yaml. Helper columns never enter authoritative exports. See docs/export-model.md.
How do I maintain the Event Log?
After a material change (a new project, a phase move, a gate outcome, a status change, a new risk or issue), append one Event Log row using config/event-mappings.yaml, or import rows. The event_evidence columns show which changes still need a row. See docs/event-capture-model.md.
What does the workbook intentionally not automate?
It does not append events, decide gates or launches, change statuses, read the clock, calculate capacity or staffing, or use AI. A named person makes every decision.
Legend: dark blue header = you edit; grey header and grey cells = formula; green header = read-only mirror of R1.

## Lookups
Lookups
Every list is synchronized from the pinned R1 version (source columns show the file). Read-only; change R1, then re-sync and rebuild.
Lookup entries (synchronized from pinned R1; read-only) | [7 empty] | Readiness weights (mirror of R1 config/readiness-weights.yaml) |  |  |  | Risk bands (mirror of R1 config/risk-rules.yaml) |  |  |  |  | Rule parameters (mirror of R1 configuration)
lookup_entry_id | lookup_type | key | display_value | source_repo | source_path | source_version | active_flag | category | weight | required_evidence | source_path | band | min_score | max_score | severity | source_path | parameter | value | source_path
LKP-000001 | phase_key | initiate | Initiate | implementation-operating-system | standard/lifecycle-terms.yaml | 9acd25a | TRUE | people | 15 | Named owners exist for every launch role, and the sponsor has confirmed availability for launch week. | config/readiness-weights.yaml | low | 1 | 4 | sev4 | config/risk-rules.yaml | risk_likelihood_min | 1 | config/risk-rules.yaml likelihood_values.min
LKP-000002 | phase_key | discover | Discover | implementation-operating-system | standard/lifecycle-terms.yaml | 9acd25a | TRUE | process | 15 | The new ways of working are documented and the sponsor has approved them. | config/readiness-weights.yaml | moderate | 5 | 9 | sev3 | config/risk-rules.yaml | risk_likelihood_max | 5 | config/risk-rules.yaml likelihood_values.max
LKP-000003 | phase_key | design | Design | implementation-operating-system | standard/lifecycle-terms.yaml | 9acd25a | TRUE | technology | 25 | Acceptance is signed off and every integration has a passing end-to-end test. | config/readiness-weights.yaml | high | 10 | 15 | sev2 | config/risk-rules.yaml | risk_impact_min | 1 | config/risk-rules.yaml impact_values.min
LKP-000004 | phase_key | build | Build | implementation-operating-system | standard/lifecycle-terms.yaml | 9acd25a | TRUE | data | 20 | The final data load plan is approved and a trial load has been checked. | config/readiness-weights.yaml | critical | 16 | 25 | sev1 | config/risk-rules.yaml | risk_impact_max | 5 | config/risk-rules.yaml impact_values.max
LKP-000005 | phase_key | validate | Validate | implementation-operating-system | standard/lifecycle-terms.yaml | 9acd25a | TRUE | training | 15 | Training completion is recorded for every user group in the training plan. | config/readiness-weights.yaml | [5 empty] | readiness_total_weight | 100 | config/readiness-weights.yaml total_weight
LKP-000006 | phase_key | enable | Enable | implementation-operating-system | standard/lifecycle-terms.yaml | 9acd25a | TRUE | support | 10 | The support runbook is published and launch-week support coverage is confirmed. | config/readiness-weights.yaml | [5 empty] | readiness_calculation_version | 1.0.0 | config/readiness-weights.yaml calculation_version
LKP-000007 | phase_key | launch | Launch | implementation-operating-system | standard/lifecycle-terms.yaml | 9acd25a | TRUE
LKP-000008 | phase_key | stabilize | Stabilize | implementation-operating-system | standard/lifecycle-terms.yaml | 9acd25a | TRUE
LKP-000009 | phase_key | transition | Transition | implementation-operating-system | standard/lifecycle-terms.yaml | 9acd25a | TRUE
LKP-000010 | phase_key | review | Review | implementation-operating-system | standard/lifecycle-terms.yaml | 9acd25a | TRUE
LKP-000011 | phase_status | not_started | not_started | implementation-operating-system | standard/lifecycle-terms.yaml | 9acd25a | TRUE
LKP-000012 | phase_status | active | active | implementation-operating-system | standard/lifecycle-terms.yaml | 9acd25a | TRUE
LKP-000013 | phase_status | awaiting_gate | awaiting_gate | implementation-operating-system | standard/lifecycle-terms.yaml | 9acd25a | TRUE
LKP-000014 | phase_status | completed | completed | implementation-operating-system | standard/lifecycle-terms.yaml | 9acd25a | TRUE
LKP-000015 | phase_status | blocked | blocked | implementation-operating-system | standard/lifecycle-terms.yaml | 9acd25a | TRUE
LKP-000016 | gate_outcome | pass | pass | implementation-operating-system | standard/lifecycle-terms.yaml | 9acd25a | TRUE
LKP-000017 | gate_outcome | pass_with_conditions | pass_with_conditions | implementation-operating-system | standard/lifecycle-terms.yaml | 9acd25a | TRUE
LKP-000018 | gate_outcome | hold | hold | implementation-operating-system | standard/lifecycle-terms.yaml | 9acd25a | TRUE
LKP-000019 | gate_id | initiate_gate | initiate | implementation-operating-system | lifecycle/gates.yaml | 9acd25a | TRUE
LKP-000020 | gate_id | discover_gate | discover | implementation-operating-system | lifecycle/gates.yaml | 9acd25a | TRUE
LKP-000021 | gate_id | design_gate | design | implementation-operating-system | lifecycle/gates.yaml | 9acd25a | TRUE
LKP-000022 | gate_id | build_gate | build | implementation-operating-system | lifecycle/gates.yaml | 9acd25a | TRUE
LKP-000023 | gate_id | validate_gate | validate | implementation-operating-system | lifecycle/gates.yaml | 9acd25a | TRUE
LKP-000024 | gate_id | enable_gate | enable | implementation-operating-system | lifecycle/gates.yaml | 9acd25a | TRUE
LKP-000025 | gate_id | launch_gate | launch | implementation-operating-system | lifecycle/gates.yaml | 9acd25a | TRUE
LKP-000026 | gate_id | stabilize_gate | stabilize | implementation-operating-system | lifecycle/gates.yaml | 9acd25a | TRUE
LKP-000027 | gate_id | transition_gate | transition | implementation-operating-system | lifecycle/gates.yaml | 9acd25a | TRUE
LKP-000028 | project_status | active | active | implementation-operating-system | schemas/project.schema.json | 9acd25a | TRUE
LKP-000029 | project_status | on_hold | on_hold | implementation-operating-system | schemas/project.schema.json | 9acd25a | TRUE
LKP-000030 | project_status | completed | completed | implementation-operating-system | schemas/project.schema.json | 9acd25a | TRUE
LKP-000031 | project_status | cancelled | cancelled | implementation-operating-system | schemas/project.schema.json | 9acd25a | TRUE
LKP-000032 | org_stage | startup | startup | implementation-operating-system | standard/org-stages.yaml | 9acd25a | TRUE
LKP-000033 | org_stage | early_scale | early_scale | implementation-operating-system | standard/org-stages.yaml | 9acd25a | TRUE
LKP-000034 | org_stage | structured_growth | structured_growth | implementation-operating-system | standard/org-stages.yaml | 9acd25a | TRUE
LKP-000035 | org_stage | mature | mature | implementation-operating-system | standard/org-stages.yaml | 9acd25a | TRUE
LKP-000036 | milestone_status | planned | planned | implementation-operating-system | schemas/milestone.schema.json | 9acd25a | TRUE
LKP-000037 | milestone_status | achieved | achieved | implementation-operating-system | schemas/milestone.schema.json | 9acd25a | TRUE
LKP-000038 | milestone_status | missed | missed | implementation-operating-system | schemas/milestone.schema.json | 9acd25a | TRUE
LKP-000039 | task_status | not_started | not_started | implementation-operating-system | schemas/task.schema.json | 9acd25a | TRUE
LKP-000040 | task_status | in_progress | in_progress | implementation-operating-system | schemas/task.schema.json | 9acd25a | TRUE
LKP-000041 | task_status | blocked | blocked | implementation-operating-system | schemas/task.schema.json | 9acd25a | TRUE
LKP-000042 | task_status | completed | completed | implementation-operating-system | schemas/task.schema.json | 9acd25a | TRUE
LKP-000043 | task_status | cancelled | cancelled | implementation-operating-system | schemas/task.schema.json | 9acd25a | TRUE
LKP-000044 | request_status | submitted | submitted | implementation-operating-system | config/request-state-machine.yaml | 9acd25a | TRUE
LKP-000045 | request_status | triaged | triaged | implementation-operating-system | config/request-state-machine.yaml | 9acd25a | TRUE
LKP-000046 | request_status | awaiting_approval | awaiting_approval | implementation-operating-system | config/request-state-machine.yaml | 9acd25a | TRUE
LKP-000047 | request_status | accepted | accepted | implementation-operating-system | config/request-state-machine.yaml | 9acd25a | TRUE
LKP-000048 | request_status | in_progress | in_progress | implementation-operating-system | config/request-state-machine.yaml | 9acd25a | TRUE
LKP-000049 | request_status | blocked | blocked | implementation-operating-system | config/request-state-machine.yaml | 9acd25a | TRUE
LKP-000050 | request_status | ready_for_handoff | ready_for_handoff | implementation-operating-system | config/request-state-machine.yaml | 9acd25a | TRUE
LKP-000051 | request_status | handed_off | handed_off | implementation-operating-system | config/request-state-machine.yaml | 9acd25a | TRUE
LKP-000052 | request_status | closed | closed | implementation-operating-system | config/request-state-machine.yaml | 9acd25a | TRUE
LKP-000053 | request_transition | submitted>triaged | owner | implementation-operating-system | config/request-state-machine.yaml | 9acd25a | TRUE
LKP-000054 | request_transition | submitted>closed | owner | implementation-operating-system | config/request-state-machine.yaml | 9acd25a | TRUE
LKP-000055 | request_transition | triaged>awaiting_approval | owner | implementation-operating-system | config/request-state-machine.yaml | 9acd25a | TRUE
LKP-000056 | request_transition | triaged>accepted | owner | implementation-operating-system | config/request-state-machine.yaml | 9acd25a | TRUE
LKP-000057 | request_transition | triaged>closed | owner | implementation-operating-system | config/request-state-machine.yaml | 9acd25a | TRUE
LKP-000058 | request_transition | awaiting_approval>accepted | approver | implementation-operating-system | config/request-state-machine.yaml | 9acd25a | TRUE
LKP-000059 | request_transition | awaiting_approval>closed | approver | implementation-operating-system | config/request-state-machine.yaml | 9acd25a | TRUE
LKP-000060 | request_transition | accepted>in_progress | owner | implementation-operating-system | config/request-state-machine.yaml | 9acd25a | TRUE
LKP-000061 | request_transition | in_progress>blocked | owner | implementation-operating-system | config/request-state-machine.yaml | 9acd25a | TRUE
LKP-000062 | request_transition | in_progress>ready_for_handoff | owner | implementation-operating-system | config/request-state-machine.yaml | 9acd25a | TRUE
LKP-000063 | request_transition | in_progress>closed | owner | implementation-operating-system | config/request-state-machine.yaml | 9acd25a | TRUE
LKP-000064 | request_transition | blocked>in_progress | owner | implementation-operating-system | config/request-state-machine.yaml | 9acd25a | TRUE
LKP-000065 | request_transition | blocked>closed | owner | implementation-operating-system | config/request-state-machine.yaml | 9acd25a | TRUE
LKP-000066 | request_transition | ready_for_handoff>handed_off | receiving_role | implementation-operating-system | config/request-state-machine.yaml | 9acd25a | TRUE
LKP-000067 | request_transition | ready_for_handoff>in_progress | owner | implementation-operating-system | config/request-state-machine.yaml | 9acd25a | TRUE
LKP-000068 | request_transition | handed_off>closed | receiving_role | implementation-operating-system | config/request-state-machine.yaml | 9acd25a | TRUE
LKP-000069 | request_type | information | information | implementation-operating-system | schemas/request.schema.json | 9acd25a | TRUE
LKP-000070 | request_type | access | access | implementation-operating-system | schemas/request.schema.json | 9acd25a | TRUE
LKP-000071 | request_type | change | change | implementation-operating-system | schemas/request.schema.json | 9acd25a | TRUE
LKP-000072 | request_type | approval | approval | implementation-operating-system | schemas/request.schema.json | 9acd25a | TRUE
LKP-000073 | request_type | data | data | implementation-operating-system | schemas/request.schema.json | 9acd25a | TRUE
LKP-000074 | request_type | training | training | implementation-operating-system | schemas/request.schema.json | 9acd25a | TRUE
LKP-000075 | request_type | support | support | implementation-operating-system | schemas/request.schema.json | 9acd25a | TRUE
LKP-000076 | request_priority | low | low | implementation-operating-system | schemas/request.schema.json | 9acd25a | TRUE
LKP-000077 | request_priority | normal | normal | implementation-operating-system | schemas/request.schema.json | 9acd25a | TRUE
LKP-000078 | request_priority | high | high | implementation-operating-system | schemas/request.schema.json | 9acd25a | TRUE
LKP-000079 | request_priority | urgent | urgent | implementation-operating-system | schemas/request.schema.json | 9acd25a | TRUE
LKP-000080 | request_source | customer | customer | implementation-operating-system | schemas/request.schema.json | 9acd25a | TRUE
LKP-000081 | request_source | internal | internal | implementation-operating-system | schemas/request.schema.json | 9acd25a | TRUE
LKP-000082 | request_source | partner | partner | implementation-operating-system | schemas/request.schema.json | 9acd25a | TRUE
LKP-000083 | handoff_status | requested | requested | implementation-operating-system | schemas/handoff.schema.json | 9acd25a | TRUE
LKP-000084 | handoff_status | accepted | accepted | implementation-operating-system | schemas/handoff.schema.json | 9acd25a | TRUE
LKP-000085 | handoff_status | rejected | rejected | implementation-operating-system | schemas/handoff.schema.json | 9acd25a | TRUE
LKP-000086 | handoff_type | intake | intake | implementation-operating-system | schemas/handoff.schema.json | 9acd25a | TRUE
LKP-000087 | handoff_type | phase | phase | implementation-operating-system | schemas/handoff.schema.json | 9acd25a | TRUE
LKP-000088 | handoff_type | request | request | implementation-operating-system | schemas/handoff.schema.json | 9acd25a | TRUE
LKP-000089 | handoff_type | transition | transition | implementation-operating-system | schemas/handoff.schema.json | 9acd25a | TRUE
LKP-000090 | risk_status | open | open | implementation-operating-system | schemas/risk.schema.json | 9acd25a | TRUE
LKP-000091 | risk_status | mitigating | mitigating | implementation-operating-system | schemas/risk.schema.json | 9acd25a | TRUE
LKP-000092 | risk_status | accepted | accepted | implementation-operating-system | schemas/risk.schema.json | 9acd25a | TRUE
LKP-000093 | risk_status | closed | closed | implementation-operating-system | schemas/risk.schema.json | 9acd25a | TRUE
LKP-000094 | issue_status | open | open | implementation-operating-system | schemas/issue.schema.json | 9acd25a | TRUE
LKP-000095 | issue_status | in_progress | in_progress | implementation-operating-system | schemas/issue.schema.json | 9acd25a | TRUE
LKP-000096 | issue_status | resolved | resolved | implementation-operating-system | schemas/issue.schema.json | 9acd25a | TRUE
LKP-000097 | issue_status | closed | closed | implementation-operating-system | schemas/issue.schema.json | 9acd25a | TRUE
LKP-000098 | severity | sev1 | Sev 1 | implementation-operating-system | standard/severity-scale.yaml | 9acd25a | TRUE
LKP-000099 | severity | sev2 | Sev 2 | implementation-operating-system | standard/severity-scale.yaml | 9acd25a | TRUE
LKP-000100 | severity | sev3 | Sev 3 | implementation-operating-system | standard/severity-scale.yaml | 9acd25a | TRUE
LKP-000101 | severity | sev4 | Sev 4 | implementation-operating-system | standard/severity-scale.yaml | 9acd25a | TRUE
LKP-000102 | readiness_category | people | People | implementation-operating-system | standard/readiness-categories.yaml | 9acd25a | TRUE
LKP-000103 | readiness_category | process | Process | implementation-operating-system | standard/readiness-categories.yaml | 9acd25a | TRUE
LKP-000104 | readiness_category | technology | Technology | implementation-operating-system | standard/readiness-categories.yaml | 9acd25a | TRUE
LKP-000105 | readiness_category | data | Data | implementation-operating-system | standard/readiness-categories.yaml | 9acd25a | TRUE
LKP-000106 | readiness_category | training | Training | implementation-operating-system | standard/readiness-categories.yaml | 9acd25a | TRUE
LKP-000107 | readiness_category | support | Support | implementation-operating-system | standard/readiness-categories.yaml | 9acd25a | TRUE
LKP-000108 | assessment_purpose | pre_assessment | pre_assessment | implementation-operating-system | schemas/readiness-scorecard.schema.json | 9acd25a | TRUE
LKP-000109 | assessment_purpose | launch_review | launch_review | implementation-operating-system | schemas/readiness-scorecard.schema.json | 9acd25a | TRUE
LKP-000110 | actor_type | human | human | implementation-operating-system | standard/schemas/event.schema.json | 9acd25a | TRUE
LKP-000111 | actor_type | system | system | implementation-operating-system | standard/schemas/event.schema.json | 9acd25a | TRUE
LKP-000112 | actor_type | ai_agent | ai_agent | implementation-operating-system | standard/schemas/event.schema.json | 9acd25a | TRUE
LKP-000113 | event_type | gate.assessed | gate_assessment | implementation-operating-system | standard/event-catalog.yaml | 9acd25a | TRUE
LKP-000114 | event_type | handoff.completed | handoff | implementation-operating-system | standard/event-catalog.yaml | 9acd25a | TRUE
LKP-000115 | event_type | improvement.logged | improvement_item | implementation-operating-system | standard/event-catalog.yaml | 9acd25a | TRUE
LKP-000116 | event_type | issue.logged | issue | implementation-operating-system | standard/event-catalog.yaml | 9acd25a | TRUE
LKP-000117 | event_type | issue.resolved | issue | implementation-operating-system | standard/event-catalog.yaml | 9acd25a | TRUE
LKP-000118 | event_type | milestone.achieved | milestone | implementation-operating-system | standard/event-catalog.yaml | 9acd25a | TRUE
LKP-000119 | event_type | milestone.missed | milestone | implementation-operating-system | standard/event-catalog.yaml | 9acd25a | TRUE
LKP-000120 | event_type | phase.entered | phase | implementation-operating-system | standard/event-catalog.yaml | 9acd25a | TRUE
LKP-000121 | event_type | phase.exited | phase | implementation-operating-system | standard/event-catalog.yaml | 9acd25a | TRUE
LKP-000122 | event_type | project.created | project | implementation-operating-system | standard/event-catalog.yaml | 9acd25a | TRUE
LKP-000123 | event_type | project.status_changed | project | implementation-operating-system | standard/event-catalog.yaml | 9acd25a | TRUE
LKP-000124 | event_type | readiness.scored | readiness_scorecard | implementation-operating-system | standard/event-catalog.yaml | 9acd25a | TRUE
LKP-000125 | event_type | request.escalated | request | implementation-operating-system | standard/event-catalog.yaml | 9acd25a | TRUE
LKP-000126 | event_type | request.status_changed | request | implementation-operating-system | standard/event-catalog.yaml | 9acd25a | TRUE
LKP-000127 | event_type | request.submitted | request | implementation-operating-system | standard/event-catalog.yaml | 9acd25a | TRUE
LKP-000128 | event_type | risk.logged | risk | implementation-operating-system | standard/event-catalog.yaml | 9acd25a | TRUE
LKP-000129 | event_type | risk.status_changed | risk | implementation-operating-system | standard/event-catalog.yaml | 9acd25a | TRUE
LKP-000130 | event_type | task.status_changed | task | implementation-operating-system | standard/event-catalog.yaml | 9acd25a | TRUE
LKP-000131 | role_id | ROL-000001 | implementation_lead | implementation-operating-system | data/synthetic/README.md | 9acd25a | TRUE
LKP-000132 | role_id | ROL-000002 | customer_sponsor | implementation-operating-system | data/synthetic/README.md | 9acd25a | TRUE
LKP-000133 | role_id | ROL-000003 | delivery_leadership | implementation-operating-system | data/synthetic/README.md | 9acd25a | TRUE
LKP-000134 | role_id | ROL-000004 | technical_specialist | implementation-operating-system | data/synthetic/README.md | 9acd25a | TRUE
LKP-000135 | role_id | ROL-000005 | enablement_lead | implementation-operating-system | data/synthetic/README.md | 9acd25a | TRUE
LKP-000136 | role_id | ROL-000006 | support_owner | implementation-operating-system | data/synthetic/README.md | 9acd25a | TRUE
LKP-000137 | role_id | ROL-000007 | customer_contact | implementation-operating-system | data/synthetic/README.md | 9acd25a | TRUE
LKP-000138 | role_id | ROL-000008 | commercial_owner | implementation-operating-system | data/synthetic/README.md | 9acd25a | TRUE
LKP-000139 | profile_id | PRF-000001 | Organization stage: startup | implementation-operating-system | profiles/examples | 9acd25a | TRUE
LKP-000140 | profile_id | PRF-000002 | Complexity tier: standard | implementation-operating-system | profiles/examples | 9acd25a | TRUE
LKP-000141 | profile_id | PRF-000003 | Service tier: standard | implementation-operating-system | profiles/examples | 9acd25a | TRUE
LKP-000142 | profile_id | PRF-000004 | Segment: mid-market | implementation-operating-system | profiles/examples | 9acd25a | TRUE
LKP-000143 | rule_id | RUL-000001 | config/sla-rules.yaml request_triage | implementation-operating-system | config | 9acd25a | TRUE
LKP-000144 | rule_id | RUL-000002 | config/sla-rules.yaml request_approval_wait | implementation-operating-system | config | 9acd25a | TRUE
LKP-000145 | rule_id | RUL-000003 | config/sla-rules.yaml request_blocked | implementation-operating-system | config | 9acd25a | TRUE
LKP-000146 | rule_id | RUL-000004 | config/sla-rules.yaml handoff_acceptance | implementation-operating-system | config | 9acd25a | TRUE
LKP-000147 | rule_id | RUL-000005 | config/sla-rules.yaml sev1 | implementation-operating-system | config | 9acd25a | TRUE
LKP-000148 | rule_id | RUL-000006 | config/sla-rules.yaml sev2 | implementation-operating-system | config | 9acd25a | TRUE
LKP-000149 | rule_id | RUL-000007 | config/sla-rules.yaml sev3 | implementation-operating-system | config | 9acd25a | TRUE
LKP-000150 | rule_id | RUL-000008 | config/sla-rules.yaml sev4 | implementation-operating-system | config | 9acd25a | TRUE
LKP-000151 | rule_id | RUL-000101 | config/lead-time-rules.yaml enable_work_before_launch | implementation-operating-system | config | 9acd25a | TRUE
LKP-000152 | rule_id | RUL-000102 | config/lead-time-rules.yaml validation_before_launch | implementation-operating-system | config | 9acd25a | TRUE
LKP-000153 | rule_id | RUL-000103 | config/lead-time-rules.yaml critical_work_before_milestone | implementation-operating-system | config | 9acd25a | TRUE
LKP-000154 | rule_id | RUL-000104 | config/lead-time-rules.yaml predecessors_finish_first | implementation-operating-system | config | 9acd25a | TRUE
LKP-000155 | rule_id | RUL-000201 | config/risk-rules.yaml risk score | implementation-operating-system | config | 9acd25a | TRUE
LKP-000156 | rule_id | RUL-000301 | config/readiness-weights.yaml readiness calculation | implementation-operating-system | config | 9acd25a | TRUE
LKP-000157 | operating_mode | starter | starter | implementation-tracker-workbook | schemas/r3/workbook-metadata.schema.json | 0.1.0 | TRUE
LKP-000158 | operating_mode | full | full | implementation-tracker-workbook | schemas/r3/workbook-metadata.schema.json | 0.1.0 | TRUE
LKP-000159 | source_entity_type | task | task | implementation-tracker-workbook | schemas/r3/capacity-input.schema.json | 0.1.0 | TRUE
LKP-000160 | source_entity_type | request | request | implementation-tracker-workbook | schemas/r3/capacity-input.schema.json | 0.1.0 | TRUE
LKP-000161 | source_entity_type | handoff | handoff | implementation-tracker-workbook | schemas/r3/capacity-input.schema.json | 0.1.0 | TRUE
LKP-000162 | source_entity_type | phase | phase | implementation-tracker-workbook | schemas/r3/capacity-input.schema.json | 0.1.0 | TRUE
LKP-000163 | workload_type | task_effort | task_effort | implementation-tracker-workbook | schemas/r3/capacity-input.schema.json | 0.1.0 | TRUE
LKP-000164 | workload_type | request_handling | request_handling | implementation-tracker-workbook | schemas/r3/capacity-input.schema.json | 0.1.0 | TRUE
LKP-000165 | workload_type | handoff_effort | handoff_effort | implementation-tracker-workbook | schemas/r3/capacity-input.schema.json | 0.1.0 | TRUE
LKP-000166 | workload_type | phase_summary | phase_summary | implementation-tracker-workbook | schemas/r3/capacity-input.schema.json | 0.1.0 | TRUE
LKP-000167 | capacity_inclusion_method | authoritative_workload | authoritative_workload | implementation-tracker-workbook | schemas/r3/capacity-input.schema.json | 0.1.0 | TRUE
LKP-000168 | capacity_inclusion_method | informational_only | informational_only | implementation-tracker-workbook | schemas/r3/capacity-input.schema.json | 0.1.0 | TRUE
LKP-000169 | capacity_inclusion_method | excluded_to_prevent_double_count | excluded_to_prevent_double_count | implementation-tracker-workbook | schemas/r3/capacity-input.schema.json | 0.1.0 | TRUE

## Projects
Projects
Grey columns are formulas (R3 checks). White columns are R1 project fields you edit.
Projects (R1 project records)
project_id | name | customer_reference | customer_label | current_phase_id | project_status | org_stage | complexity_profile_id | service_profile_id | segment_profile_id | project_owner_role_id | target_launch_date | actual_launch_date | external_reference | created_at | updated_at | schema_version | current_phase_key | reference_check | event_evidence
PRJ-000001 | Synthetic Project A | SYN-CUSTOMER-A | Synthetic Organization A | PHS-000002 | active | startup | PRF-000002 | PRF-000003 | PRF-000004 | ROL-000001 | 2026-12-01 |  |  | 2026-09-08T14:00:00Z | 2026-10-01T15:00:00Z | 0.1.0
PRJ-000002 | Synthetic Project B | SYN-CUSTOMER-B | Synthetic Organization B | PHS-000006 | active | early_scale | PRF-000002 | PRF-000003 | PRF-000004 | ROL-000001 | 2026-11-16 |  | SYN-INTAKE-B | 2026-06-01T15:00:00Z | 2026-10-05T16:00:00Z | 0.1.0
PRJ-000003 | Synthetic Project C | SYN-CUSTOMER-C | Synthetic Organization C | PHS-000015 | active | structured_growth | PRF-000002 | PRF-000003 | PRF-000004 | ROL-000001 | 2026-10-19 |  | SYN-INTAKE-C | 2026-03-02T15:00:00Z | 2026-10-05T14:00:00Z | 0.1.0

## Phases and Gates
Phases and Gates
A person records every gate outcome in tblGateAssessments. The workbook checks values; it never decides a gate.
Phases (R1 phase instances) | [11 empty] | Milestones (R1 milestone records) | [11 empty] | Gate assessments (R1 records; a person records every outcome)
phase_id | project_id | lifecycle_phase_key | status | entered_at | exited_at | owner_role_id | gate_id | schema_version | reference_check | gate_check | event_evidence | milestone_id | project_id | phase_id | name | status | target_date | completed_date | critical_flag | owner_role_id | schema_version | reference_check | event_evidence | gate_assessment_id | gate_id | project_id | phase_id | outcome | assessed_at | assessor_person_id | evidence_types_provided | evidence_refs | condition_refs | reason | schema_version | outcome_check | assessor_check | reference_check | event_evidence
PHS-000001 | PRJ-000001 | initiate | completed | 2026-09-08T14:05:00Z | 2026-09-15T16:00:00Z | ROL-000001 | initiate_gate | 0.1.0 |  |  |  | MLS-000001 | PRJ-000001 | PHS-000001 | Kickoff completed | achieved | 2026-09-11 | 2026-09-10 | TRUE | ROL-000001 | 0.1.0 |  |  | GAT-000002 | design_gate | PRJ-000002 | PHS-000005 | pass_with_conditions | 2026-09-11T14:30:00Z | PER-000002 | solution_design;design_approval | MLS-000004;TSK-000007 | RSK-000002 | Design approved. Integration access is not yet confirmed and is tracked as a risk. | 0.1.0
PHS-000002 | PRJ-000001 | discover | active | 2026-09-15T16:05:00Z |  | ROL-000001 | discover_gate | 0.1.0 |  |  |  | MLS-000002 | PRJ-000001 | PHS-000002 | Current-state discovery signed off | planned | 2026-10-09 |  | TRUE | ROL-000001 | 0.1.0
PHS-000003 | PRJ-000002 | initiate | completed | 2026-06-01T15:05:00Z | 2026-06-12T17:00:00Z | ROL-000001 | initiate_gate | 0.1.0 |  |  |  | MLS-000003 | PRJ-000002 | PHS-000003 | Kickoff completed | achieved | 2026-06-05 | 2026-06-04 | TRUE | ROL-000001 | 0.1.0
PHS-000004 | PRJ-000002 | discover | completed | 2026-06-12T17:05:00Z | 2026-07-03T16:00:00Z | ROL-000001 | discover_gate | 0.1.0 |  |  |  | MLS-000004 | PRJ-000002 | PHS-000005 | Design approved | achieved | 2026-08-14 | 2026-09-10 | TRUE | ROL-000001 | 0.1.0
PHS-000005 | PRJ-000002 | design | completed | 2026-07-03T16:05:00Z | 2026-09-11T15:00:00Z | ROL-000001 | design_gate | 0.1.0 |  |  |  | MLS-000005 | PRJ-000002 | PHS-000006 | Integration build complete | missed | 2026-10-02 |  | TRUE | ROL-000004 | 0.1.0
PHS-000006 | PRJ-000002 | build | active | 2026-09-11T15:05:00Z |  | ROL-000004 | build_gate | 0.1.0 |  |  |  | MLS-000006 | PRJ-000002 | PHS-000006 | Configuration build complete | planned | 2026-10-16 |  | FALSE | ROL-000004 | 0.1.0
PHS-000007 | PRJ-000003 | initiate | completed | 2026-03-02T15:05:00Z | 2026-03-13T17:00:00Z | ROL-000001 | initiate_gate | 0.1.0 |  |  |  | MLS-000007 | PRJ-000003 | PHS-000007 | Kickoff completed | achieved | 2026-03-06 | 2026-03-05 | TRUE | ROL-000001 | 0.1.0
PHS-000008 | PRJ-000003 | discover | completed | 2026-03-13T17:05:00Z | 2026-04-10T16:00:00Z | ROL-000001 | discover_gate | 0.1.0 |  |  |  | MLS-000008 | PRJ-000003 | PHS-000009 | Design approved | achieved | 2026-05-15 | 2026-05-14 | TRUE | ROL-000001 | 0.1.0
PHS-000009 | PRJ-000003 | design | completed | 2026-04-10T16:05:00Z | 2026-05-15T16:00:00Z | ROL-000001 | design_gate | 0.1.0 |  |  |  | MLS-000009 | PRJ-000003 | PHS-000012 | Build complete | achieved | 2026-08-21 | 2026-08-21 | TRUE | ROL-000004 | 0.1.0
PHS-000010 | PRJ-000003 | build | completed | 2026-05-15T16:05:00Z | 2026-07-10T16:00:00Z | ROL-000004 | build_gate | 0.1.0 |  |  |  | MLS-000010 | PRJ-000003 | PHS-000013 | User acceptance signed off | achieved | 2026-09-11 | 2026-09-11 | TRUE | ROL-000001 | 0.1.0
PHS-000011 | PRJ-000003 | validate | completed | 2026-07-10T16:05:00Z | 2026-07-31T16:00:00Z | ROL-000001 | validate_gate | 0.1.0 |  |  |  | MLS-000011 | PRJ-000003 | PHS-000014 | Training delivered | achieved | 2026-09-26 | 2026-09-29 | TRUE | ROL-000005 | 0.1.0
PHS-000012 | PRJ-000003 | build | completed | 2026-07-31T16:05:00Z | 2026-08-21T16:00:00Z | ROL-000004 | build_gate | 0.1.0 |  |  |  | MLS-000012 | PRJ-000003 | PHS-000015 | Launch completed | planned | 2026-10-19 |  | TRUE | ROL-000001 | 0.1.0
PHS-000013 | PRJ-000003 | validate | completed | 2026-08-21T16:05:00Z | 2026-09-11T14:00:00Z | ROL-000001 | validate_gate | 0.1.0
PHS-000014 | PRJ-000003 | enable | completed | 2026-09-11T14:05:00Z | 2026-09-30T15:00:00Z | ROL-000005 | enable_gate | 0.1.0
PHS-000015 | PRJ-000003 | launch | awaiting_gate | 2026-09-30T15:05:00Z |  | ROL-000001 | launch_gate | 0.1.0

## Tasks
Tasks
due_state uses calculation_as_of_at on the README tab, never the clock.
Tasks (R1 task records)
task_id | project_id | phase_id | milestone_id | name | status | owner_role_id | planned_hours | actual_hours | predecessor_task_ids | planned_start_date | planned_due_date | completed_at | critical_flag | schema_version | due_state | predecessor_reference_valid | reference_check | event_evidence
TSK-000001 | PRJ-000001 | PHS-000001 | MLS-000001 | Confirm scope and success criteria | completed | ROL-000001 | 3 | 2.5 |  | 2026-09-08 | 2026-09-10 | 2026-09-10T17:00:00Z | TRUE | 0.1.0
TSK-000002 | PRJ-000001 | PHS-000001 | MLS-000001 | Run kickoff session | completed | ROL-000001 | 2 | 2 | TSK-000001 | 2026-09-10 | 2026-09-11 | 2026-09-10T20:00:00Z | TRUE | 0.1.0
TSK-000003 | PRJ-000001 | PHS-000002 | MLS-000002 | Collect current-state inventory | completed | ROL-000001 | 6 | 7 | TSK-000002 | 2026-09-15 | 2026-09-25 | 2026-09-25T18:00:00Z | TRUE | 0.1.0
TSK-000004 | PRJ-000001 | PHS-000002 | MLS-000002 | Map current process steps | in_progress | ROL-000001 | 8 | 5 | TSK-000003 | 2026-09-28 | 2026-10-07 |  | TRUE | 0.1.0
TSK-000005 | PRJ-000001 | PHS-000002 | MLS-000002 | Document data sources | not_started | ROL-000004 | 4 |  | TSK-000003 | 2026-10-01 | 2026-10-08 |  | FALSE | 0.1.0
TSK-000006 | PRJ-000001 | PHS-000002 | MLS-000002 | Draft discovery summary | not_started | ROL-000001 | 3 |  | TSK-000004;TSK-000005 | 2026-10-07 | 2026-10-09 |  | TRUE | 0.1.0
TSK-000007 | PRJ-000002 | PHS-000005 | MLS-000004 | Approve solution design | completed | ROL-000001 | 6 | 9 |  | 2026-07-20 | 2026-08-14 | 2026-09-10T16:00:00Z | TRUE | 0.1.0
TSK-000008 | PRJ-000002 | PHS-000006 | MLS-000006 | Set up build environment access | completed | ROL-000004 | 4 | 4 | TSK-000007 | 2026-09-11 | 2026-09-15 | 2026-09-15T17:00:00Z | TRUE | 0.1.0
TSK-000009 | PRJ-000002 | PHS-000006 | MLS-000006 | Configure core records | in_progress | ROL-000004 | 16 | 10 | TSK-000008 | 2026-09-15 | 2026-10-09 |  | TRUE | 0.1.0
TSK-000010 | PRJ-000002 | PHS-000006 | MLS-000006 | Configure user roles | completed | ROL-000004 | 6 | 5 | TSK-000008 | 2026-09-15 | 2026-09-22 | 2026-09-22T18:00:00Z | FALSE | 0.1.0
TSK-000011 | PRJ-000002 | PHS-000006 | MLS-000005 | Obtain integration credentials from the customer | blocked | ROL-000001 | 4 | 2 | TSK-000008 | 2026-09-16 | 2026-09-25 |  | TRUE | 0.1.0
TSK-000012 | PRJ-000002 | PHS-000006 | MLS-000005 | Build integration mappings | not_started | ROL-000004 | 12 |  | TSK-000011 | 2026-09-25 | 2026-09-30 |  | TRUE | 0.1.0
TSK-000013 | PRJ-000002 | PHS-000006 | MLS-000005 | Test integration end to end | not_started | ROL-000004 | 6 |  | TSK-000012 | 2026-09-30 | 2026-10-02 |  | TRUE | 0.1.0
TSK-000014 | PRJ-000002 | PHS-000006 | MLS-000006 | Load reference data | in_progress | ROL-000004 | 8 | 3 | TSK-000010 | 2026-09-22 | 2026-10-09 |  | FALSE | 0.1.0
TSK-000015 | PRJ-000002 | PHS-000006 | MLS-000006 | Prepare validation scenarios | not_started | ROL-000001 | 5 |  | TSK-000009 | 2026-10-09 | 2026-10-16 |  | FALSE | 0.1.0
TSK-000016 | PRJ-000002 | PHS-000006 |  | Update risk entries after the design change | completed | ROL-000001 | 1 | 1.5 |  | 2026-09-11 | 2026-09-12 | 2026-09-12T15:00:00Z | FALSE | 0.1.0
TSK-000017 | PRJ-000003 | PHS-000009 | MLS-000008 | Approve solution design | completed | ROL-000001 | 8 | 8 |  | 2026-04-27 | 2026-05-14 | 2026-05-14T16:00:00Z | TRUE | 0.1.0
TSK-000018 | PRJ-000003 | PHS-000010 | MLS-000009 | Configure core records | completed | ROL-000004 | 24 | 28 | TSK-000017 | 2026-05-15 | 2026-06-19 | 2026-06-19T17:00:00Z | TRUE | 0.1.0
TSK-000019 | PRJ-000003 | PHS-000010 | MLS-000009 | Build integrations | completed | ROL-000004 | 20 | 26 | TSK-000017 | 2026-05-15 | 2026-07-03 | 2026-07-08T17:00:00Z | TRUE | 0.1.0
TSK-000020 | PRJ-000003 | PHS-000011 | MLS-000010 | Run first acceptance test cycle | completed | ROL-000001 | 12 | 14 | TSK-000018;TSK-000019 | 2026-07-10 | 2026-07-24 | 2026-07-29T17:00:00Z | TRUE | 0.1.0
TSK-000021 | PRJ-000003 | PHS-000012 | MLS-000009 | Fix defects from the first test cycle | completed | ROL-000004 | 16 | 18 | TSK-000020 | 2026-07-31 | 2026-08-19 | 2026-08-20T17:00:00Z | TRUE | 0.1.0
TSK-000022 | PRJ-000003 | PHS-000013 | MLS-000010 | Run second acceptance test cycle | completed | ROL-000001 | 10 | 9 | TSK-000021 | 2026-08-21 | 2026-09-09 | 2026-09-10T17:00:00Z | TRUE | 0.1.0
TSK-000023 | PRJ-000003 | PHS-000014 | MLS-000011 | Train customer administrators | completed | ROL-000005 | 8 | 8 | TSK-000022 | 2026-09-14 | 2026-09-22 | 2026-09-22T19:00:00Z | TRUE | 0.1.0
TSK-000024 | PRJ-000003 | PHS-000014 | MLS-000011 | Train end users | completed | ROL-000005 | 12 | 13 | TSK-000023 | 2026-09-22 | 2026-09-26 | 2026-09-29T19:00:00Z | TRUE | 0.1.0
TSK-000025 | PRJ-000003 | PHS-000014 | MLS-000012 | Publish support runbook | completed | ROL-000006 | 6 | 6 | TSK-000022 | 2026-09-14 | 2026-09-25 | 2026-09-25T17:00:00Z | FALSE | 0.1.0
TSK-000026 | PRJ-000003 | PHS-000015 | MLS-000012 | Validate final data load plan | completed | ROL-000004 | 8 | 8 | TSK-000022 | 2026-09-30 | 2026-10-01 | 2026-10-01T16:00:00Z | TRUE | 0.1.0
TSK-000027 | PRJ-000003 | PHS-000015 | MLS-000012 | Confirm support coverage for launch week | completed | ROL-000006 | 3 | 3 | TSK-000025 | 2026-09-30 | 2026-10-01 | 2026-10-01T17:00:00Z | TRUE | 0.1.0
TSK-000028 | PRJ-000003 | PHS-000015 | MLS-000012 | Prepare launch readiness review | completed | ROL-000001 | 4 | 4 | TSK-000024;TSK-000025 | 2026-09-30 | 2026-10-02 | 2026-10-02T14:00:00Z | TRUE | 0.1.0
TSK-000029 | PRJ-000003 | PHS-000015 | MLS-000012 | Collect remaining training sign-offs | in_progress | ROL-000005 | 3 | 1.5 | TSK-000024 | 2026-09-30 | 2026-10-09 |  | FALSE | 0.1.0
TSK-000030 | PRJ-000003 | PHS-000015 | MLS-000012 | Schedule post-launch check-ins | not_started | ROL-000001 | 2 |  | TSK-000028 | 2026-10-12 | 2026-10-16 |  | FALSE | 0.1.0

## Requests and Handoffs
Requests and Handoffs
Statuses and legal transitions come from R1 config/request-state-machine.yaml. Escalation times come from R1 config/sla-rules.yaml.
Requests (R1 request records; statuses from R1 config/request-state-machine.yaml) | [19 empty] | Handoffs (R1 handoff records)
request_id | project_id | request_type | status | submitted_at | submitted_by_role_id | owner_role_id | priority | due_at | status_changed_at | escalation_due_at | source | description | schema_version | status_check | escalation_rule_id | escalation_due_check | escalation_due_state | reference_check | event_evidence | handoff_id | project_id | from_role_id | to_role_id | handoff_type | status | required_artifact_refs | open_item_refs | requested_at | accepted_at | acceptance_person_id | schema_version | status_check | acceptance_check | reference_check | event_evidence
REQ-000001 | PRJ-000001 | information | in_progress | 2026-09-16T15:00:00Z | ROL-000002 | ROL-000001 | normal | 2026-10-07T17:00:00Z | 2026-09-18T14:00:00Z |  | customer | Confirm which current-state reports are still used. | 0.1.0 | [6 empty] | HND-000002 | PRJ-000003 | ROL-000004 | ROL-000006 | request | accepted | REQ-000006 | ISS-000005 | 2026-10-02T14:00:00Z | 2026-10-02T17:00:00Z | PER-000005 | 0.1.0
REQ-000002 | PRJ-000002 | access | blocked | 2026-09-15T17:00:00Z | ROL-000002 | ROL-000004 | high | 2026-09-30T17:00:00Z | 2026-09-24T15:00:00Z | 2026-09-26T15:00:00Z | customer | Set up the integration connection to the customer system. | 0.1.0
REQ-000003 | PRJ-000002 | approval | awaiting_approval | 2026-10-02T14:00:00Z | ROL-000004 | ROL-000002 | normal | 2026-10-09T17:00:00Z | 2026-10-03T15:00:00Z | 2026-10-06T15:00:00Z | internal | Approve a change to the user role design found during build. | 0.1.0
REQ-000004 | PRJ-000002 | information | triaged | 2026-10-05T13:00:00Z | ROL-000004 | ROL-000007 | normal | 2026-10-08T17:00:00Z | 2026-10-05T16:00:00Z |  | internal | Clarify the format of the reference data file. | 0.1.0
REQ-000005 | PRJ-000003 | change | closed | 2026-09-14T14:00:00Z | ROL-000007 | ROL-000004 | low | 2026-09-21T17:00:00Z | 2026-09-19T16:00:00Z |  | customer | Adjust the wording of two notifications. | 0.1.0
REQ-000006 | PRJ-000003 | data | handed_off | 2026-09-22T14:00:00Z | ROL-000002 | ROL-000004 | high | 2026-10-05T17:00:00Z | 2026-10-02T17:05:00Z |  | customer | Prepare the procedure for the final data extract and hand it to the support team. | 0.1.0
REQ-000007 | PRJ-000003 | information | accepted | 2026-10-01T15:00:00Z | ROL-000001 | ROL-000006 | normal | 2026-10-08T17:00:00Z | 2026-10-01T18:00:00Z |  | internal | Provide the after-hours contact list for launch week. | 0.1.0
REQ-000008 | PRJ-000003 | information | submitted | 2026-10-05T14:00:00Z | ROL-000007 | ROL-000001 | normal | 2026-10-09T17:00:00Z | 2026-10-05T14:00:00Z | 2026-10-06T14:00:00Z | customer | Explain how report access will work after launch. | 0.1.0

## Escalation Rules
Escalation Rules
Source of truth: R1 configuration. This tab is a read-only mirror; editing it would not change R1.
Escalation and lead-time rules (mirror; source of truth: R1 configuration)
rule_id | source_file | source_version | rule_kind | rule_key | applies_to | trigger | duration_parameter | duration_hours | warning_behavior | escalation_role_id | escalation_severity | action | enabled | stage_behavior | match_key
RUL-000001 | config/sla-rules.yaml | 9acd25a | sla | request_triage | request | status=submitted | PT24H | 24 | warning PT4H before due | ROL-000001 | sev3 | escalate | TRUE | startup=optional; early_scale=recommended; structured_growth=required; mature=required | request¦submitted
RUL-000002 | config/sla-rules.yaml | 9acd25a | sla | request_approval_wait | request | status=awaiting_approval | PT72H | 72 | warning PT24H before due | ROL-000003 | sev3 | escalate | TRUE | startup=optional; early_scale=recommended; structured_growth=required; mature=required | request¦awaiting_approval
RUL-000003 | config/sla-rules.yaml | 9acd25a | sla | request_blocked | request | status=blocked | PT48H | 48 | warning PT8H before due | ROL-000003 | sev2 | escalate | TRUE | startup=recommended; early_scale=required; structured_growth=required; mature=required | request¦blocked
RUL-000004 | config/sla-rules.yaml | 9acd25a | sla | handoff_acceptance | handoff | status=requested | PT72H | 72 | warning PT24H before due | ROL-000003 |  | notify_role | TRUE | startup=optional; early_scale=recommended; structured_growth=required; mature=required | handoff¦requested¦¦notify_role
RUL-000005 | config/sla-rules.yaml | 9acd25a | sla | sev1 | issue | status=open; severity=sev1 | PT1H | 1 | warning PT15M before due | ROL-000003 |  | notify_role | TRUE | startup=required; early_scale=required; structured_growth=required; mature=required | issue¦open¦sev1¦notify_role
RUL-000006 | config/sla-rules.yaml | 9acd25a | sla | sev2 | issue | status=open; severity=sev2 | PT4H | 4 | warning PT1H before due | ROL-000001 |  | notify_role | TRUE | startup=recommended; early_scale=required; structured_growth=required; mature=required | issue¦open¦sev2¦notify_role
RUL-000007 | config/sla-rules.yaml | 9acd25a | sla | sev3 | issue | status=open; severity=sev3 | PT24H | 24 | warning PT4H before due |  |  | notify_owner | TRUE | startup=optional; early_scale=recommended; structured_growth=required; mature=required | issue¦open¦sev3¦notify_owner
RUL-000008 | config/sla-rules.yaml | 9acd25a | sla | sev4 | issue | status=open; severity=sev4 | PT72H | 72 | warning PT24H before due |  |  | notify_owner | TRUE | startup=optional; early_scale=optional; structured_growth=recommended; mature=recommended | issue¦open¦sev4¦notify_owner
RUL-000101 | config/lead-time-rules.yaml | 9acd25a | lead_time | enable_work_before_launch | task | due_before_target_launch; phase_keys=enable; critical_only=true; open_only=false | P5D | 120 | flag only; no warning timer |  |  | flag | TRUE | not set in R1 for lead-time rules | task¦due_before_target_launch¦RUL-000101
RUL-000102 | config/lead-time-rules.yaml | 9acd25a | lead_time | validation_before_launch | task | due_before_target_launch; phase_keys=validate; critical_only=false; open_only=false | P10D | 240 | flag only; no warning timer |  |  | flag | TRUE | not set in R1 for lead-time rules | task¦due_before_target_launch¦RUL-000102
RUL-000103 | config/lead-time-rules.yaml | 9acd25a | lead_time | critical_work_before_milestone | task | due_before_milestone; phase_keys=all; critical_only=true; open_only=false | P0D | 0 | flag only; no warning timer |  |  | flag | TRUE | not set in R1 for lead-time rules | task¦due_before_milestone¦RUL-000103
RUL-000104 | config/lead-time-rules.yaml | 9acd25a | lead_time | predecessors_finish_first | task | start_after_predecessors; phase_keys=all; critical_only=false; open_only=true | P0D | 0 | flag only; no warning timer |  |  | flag | TRUE | not set in R1 for lead-time rules | task¦start_after_predecessors¦RUL-000104

## Risks and Issues
Risks and Issues
risk_score is calculated (likelihood x impact on the R1 scale); never type it. Severity values come from the R1 standard.
Risks (R1 risk records; risk_score is calculated, never typed) | [17 empty] | Issues (R1 issue records; severity from R1 standard)
risk_id | project_id | phase_id | title | description | likelihood | impact | risk_score | status | owner_role_id | mitigation | identified_at | resolved_at | schema_version | risk_band | risk_severity | reference_check | event_evidence | issue_id | project_id | phase_id | title | description | severity | status | owner_role_id | opened_at | resolved_at | resolution | schema_version | severity_check | reference_check | event_evidence
RSK-000001 | PRJ-000001 | PHS-000002 | Key stakeholders have limited time during discovery | Discovery sessions may slip if the customer's process owners are unavailable. | 3 | 2 |  | open | ROL-000001 | Book discovery sessions two weeks ahead and share agendas early. | 2026-09-17T15:00:00Z |  | 0.1.0 |  |  |  |  | ISS-000001 | PRJ-000002 | PHS-000006 | Build environment access expired for one specialist | One technical specialist could not sign in to the build environment. | sev3 | resolved | ROL-000004 | 2026-09-14T14:00:00Z | 2026-09-15T11:00:00Z | Access was renewed by the customer contact. | 0.1.0
RSK-000002 | PRJ-000002 | PHS-000005 | Integration access may be delayed | Customer credentials for the integration may not arrive before build starts. | 4 | 3 |  | mitigating | ROL-000001 | Request access early and escalate through the blocked-request rule. | 2026-09-10T15:00:00Z |  | 0.1.0 |  |  |  |  | ISS-000002 | PRJ-000002 | PHS-000006 | Integration cannot be tested without credentials | End-to-end integration testing is stopped until access is provided. | sev2 | in_progress | ROL-000004 | 2026-09-24T17:00:00Z |  |  | 0.1.0
RSK-000003 | PRJ-000002 | PHS-000006 | Reference data quality is unknown | The reference data file has not been checked and may need cleanup before loading. | 3 | 3 |  | open | ROL-000004 | Run a sample load and review errors with the customer contact. | 2026-09-22T15:00:00Z |  | 0.1.0 |  |  |  |  | ISS-000003 | PRJ-000003 | PHS-000013 | Two report filters return wrong totals | Two filters double-count records during acceptance testing. | sev3 | closed | ROL-000004 | 2026-09-02T14:00:00Z | 2026-09-08T16:00:00Z | Filter logic was corrected and retested. | 0.1.0
RSK-000004 | PRJ-000002 | PHS-000004 | Sponsor may change during discovery | A change of customer sponsor could reopen agreed requirements. | 2 | 4 |  | closed | ROL-000001 | Confirmed the sponsor for the full project with the customer. | 2026-06-20T15:00:00Z | 2026-07-03T15:00:00Z | 0.1.0 |  |  |  |  | ISS-000004 | PRJ-000003 | PHS-000014 | Training environment slow during sessions | Pages load slowly when more than one class uses the training environment. | sev3 | resolved | ROL-000004 | 2026-09-21T14:00:00Z | 2026-09-23T16:00:00Z | Classes were moved to separate time slots. | 0.1.0
RSK-000005 | PRJ-000003 | PHS-000014 | End-user training may be incomplete before launch | Some user groups may not finish training before the launch date. | 3 | 4 |  | mitigating | ROL-000005 | Add a make-up session and track sign-offs daily. | 2026-09-18T15:00:00Z |  | 0.1.0 |  |  |  |  | ISS-000005 | PRJ-000003 | PHS-000015 | Final data extract arrives one day late | The customer's final extract is scheduled one day after the planned date. | sev4 | open | ROL-000004 | 2026-10-01T14:00:00Z |  |  | 0.1.0
RSK-000006 | PRJ-000003 | PHS-000013 | Final data load could overlap launch week | The final data load window is close to the launch date. | 2 | 5 |  | accepted | ROL-000004 | The sponsor accepted the timing; the load plan includes a fallback step. | 2026-09-08T15:00:00Z |  | 0.1.0

## Readiness Scorecard
Readiness Scorecard
Readiness score informs human review. It does not decide go or no-go.
Readiness entries (R1 readiness rows; calculated columns reproduce R1) | [18 empty] | Readiness summary (one row per scorecard)
readiness_entry_id | readiness_scorecard_id | project_id | assessment_purpose | assessed_at | calculation_version | category | weight | criteria_total_count | criteria_met_count | achieved_rate | category_score | required_evidence_complete_flag | evidence_refs | overall_score | incomplete_required_evidence_flag | schema_version | weighted_result | category_count_check | readiness_scorecard_id | project_id | assessment_purpose | assessed_at | overall_score | incomplete_required_evidence_flag | evidence_warning | event_evidence
RDE-000001 | RDS-000001 | PRJ-000001 | pre_assessment | 2026-10-01T15:00:00Z | 1.0.0 | people |  | 4 | 2 |  |  | FALSE | MLS-000001 |  |  | 0.1.0 |  |  | RDS-000001
RDE-000002 | RDS-000001 | PRJ-000001 | pre_assessment | 2026-10-01T15:00:00Z | 1.0.0 | process |  | 4 | 1 |  |  | FALSE | TSK-000001 |  |  | 0.1.0 |  |  | RDS-000002
RDE-000003 | RDS-000001 | PRJ-000001 | pre_assessment | 2026-10-01T15:00:00Z | 1.0.0 | technology |  | 5 | 0 |  |  | FALSE |  |  |  | 0.1.0 |  |  | RDS-000003
RDE-000004 | RDS-000001 | PRJ-000001 | pre_assessment | 2026-10-01T15:00:00Z | 1.0.0 | data |  | 4 | 1 |  |  | FALSE | TSK-000003 |  |  | 0.1.0
RDE-000005 | RDS-000001 | PRJ-000001 | pre_assessment | 2026-10-01T15:00:00Z | 1.0.0 | training |  | 4 | 0 |  |  | FALSE |  |  |  | 0.1.0
RDE-000006 | RDS-000001 | PRJ-000001 | pre_assessment | 2026-10-01T15:00:00Z | 1.0.0 | support |  | 4 | 0 |  |  | FALSE |  |  |  | 0.1.0
RDE-000007 | RDS-000002 | PRJ-000002 | pre_assessment | 2026-10-01T16:00:00Z | 1.0.0 | people |  | 4 | 3 |  |  | TRUE | MLS-000003 |  |  | 0.1.0
RDE-000008 | RDS-000002 | PRJ-000002 | pre_assessment | 2026-10-01T16:00:00Z | 1.0.0 | process |  | 4 | 3 |  |  | TRUE | MLS-000004 |  |  | 0.1.0
RDE-000009 | RDS-000002 | PRJ-000002 | pre_assessment | 2026-10-01T16:00:00Z | 1.0.0 | technology |  | 5 | 2 |  |  | FALSE | TSK-000008;TSK-000010 |  |  | 0.1.0
RDE-000010 | RDS-000002 | PRJ-000002 | pre_assessment | 2026-10-01T16:00:00Z | 1.0.0 | data |  | 4 | 1 |  |  | FALSE | TSK-000014 |  |  | 0.1.0
RDE-000011 | RDS-000002 | PRJ-000002 | pre_assessment | 2026-10-01T16:00:00Z | 1.0.0 | training |  | 4 | 0 |  |  | FALSE |  |  |  | 0.1.0
RDE-000012 | RDS-000002 | PRJ-000002 | pre_assessment | 2026-10-01T16:00:00Z | 1.0.0 | support |  | 4 | 0 |  |  | FALSE |  |  |  | 0.1.0
RDE-000013 | RDS-000003 | PRJ-000003 | launch_review | 2026-10-02T15:00:00Z | 1.0.0 | people |  | 4 | 4 |  |  | TRUE | TSK-000028 |  |  | 0.1.0
RDE-000014 | RDS-000003 | PRJ-000003 | launch_review | 2026-10-02T15:00:00Z | 1.0.0 | process |  | 4 | 4 |  |  | TRUE | MLS-000008 |  |  | 0.1.0
RDE-000015 | RDS-000003 | PRJ-000003 | launch_review | 2026-10-02T15:00:00Z | 1.0.0 | technology |  | 5 | 5 |  |  | TRUE | MLS-000010;TSK-000022 |  |  | 0.1.0
RDE-000016 | RDS-000003 | PRJ-000003 | launch_review | 2026-10-02T15:00:00Z | 1.0.0 | data |  | 4 | 3 |  |  | TRUE | TSK-000026 |  |  | 0.1.0
RDE-000017 | RDS-000003 | PRJ-000003 | launch_review | 2026-10-02T15:00:00Z | 1.0.0 | training |  | 4 | 3 |  |  | FALSE | MLS-000011;TSK-000024 |  |  | 0.1.0
RDE-000018 | RDS-000003 | PRJ-000003 | launch_review | 2026-10-02T15:00:00Z | 1.0.0 | support |  | 4 | 4 |  |  | TRUE | TSK-000025;TSK-000027 |  |  | 0.1.0

## Capacity Inputs
Capacity Inputs
Prepares workload hours for future capacity planning. It does not calculate capacity, utilization, staffing need, hiring timing, or capacity gap.
Capacity inputs (R3 export for future R2; no capacity math here) | [18 empty] | Capacity input checks (R3 view; not capacity, utilization, or staffing)
capacity_input_id | period | project_id | source_entity_type | source_entity_id | role_id | workload_component_id | workload_type | planned_hours | actual_hours | unit | capacity_inclusion_method | source_repo | source_version | org_stage | export_ready_flag | duplicate_authoritative_flag | authoritative_planned_hours | authoritative_actual_hours | check_key | value | meaning
CPI-000001 |  |  | task | TSK-000001 |  | TSK-000001 | task_effort |  |  | hours | authoritative_workload | implementation-operating-system | 9acd25a | [5 empty] | authoritative_planned_hours_total |  | Planned hours counted once, from authoritative rows only.
CPI-000002 |  |  | task | TSK-000002 |  | TSK-000002 | task_effort |  |  | hours | authoritative_workload | implementation-operating-system | 9acd25a | [5 empty] | authoritative_actual_hours_total |  | Actual hours counted once, from authoritative rows only.
CPI-000003 |  |  | task | TSK-000003 |  | TSK-000003 | task_effort |  |  | hours | authoritative_workload | implementation-operating-system | 9acd25a | [5 empty] | task_planned_hours_total |  | Planned hours on the Tasks tab, for reconciliation.
CPI-000004 |  |  | task | TSK-000004 |  | TSK-000004 | task_effort |  |  | hours | authoritative_workload | implementation-operating-system | 9acd25a | [5 empty] | task_actual_hours_total |  | Actual hours on the Tasks tab, for reconciliation.
CPI-000005 |  |  | task | TSK-000005 |  | TSK-000005 | task_effort |  |  | hours | authoritative_workload | implementation-operating-system | 9acd25a | [5 empty] | hours_reconciliation |  | reconciled when authoritative totals equal the task totals: every task counted exactly once.
CPI-000006 |  |  | task | TSK-000006 |  | TSK-000006 | task_effort |  |  | hours | authoritative_workload | implementation-operating-system | 9acd25a | [5 empty] | authoritative_row_count |  | Rows that carry authoritative workload.
CPI-000007 |  |  | task | TSK-000007 |  | TSK-000007 | task_effort |  |  | hours | authoritative_workload | implementation-operating-system | 9acd25a | [5 empty] | informational_row_count |  | Rows exported for context; ignored by capacity math.
CPI-000008 |  |  | task | TSK-000008 |  | TSK-000008 | task_effort |  |  | hours | authoritative_workload | implementation-operating-system | 9acd25a | [5 empty] | excluded_row_count |  | Rows that repeat a task's work and are excluded.
CPI-000009 |  |  | task | TSK-000009 |  | TSK-000009 | task_effort |  |  | hours | authoritative_workload | implementation-operating-system | 9acd25a | [5 empty] | duplicate_authoritative_count |  | Rows claiming an already-authoritative component; must be 0.
CPI-000010 |  |  | task | TSK-000010 |  | TSK-000010 | task_effort |  |  | hours | authoritative_workload | implementation-operating-system | 9acd25a | [5 empty] | tasks_without_authoritative_row |  | Tasks with no authoritative capacity row; must be 0 before export.
CPI-000011 |  |  | task | TSK-000011 |  | TSK-000011 | task_effort |  |  | hours | authoritative_workload | implementation-operating-system | 9acd25a | [5 empty] | export_ready_row_count |  | Rows ready to export.
CPI-000012 |  |  | task | TSK-000012 |  | TSK-000012 | task_effort |  |  | hours | authoritative_workload | implementation-operating-system | 9acd25a
CPI-000013 |  |  | task | TSK-000013 |  | TSK-000013 | task_effort |  |  | hours | authoritative_workload | implementation-operating-system | 9acd25a
CPI-000014 |  |  | task | TSK-000014 |  | TSK-000014 | task_effort |  |  | hours | authoritative_workload | implementation-operating-system | 9acd25a
CPI-000015 |  |  | task | TSK-000015 |  | TSK-000015 | task_effort |  |  | hours | authoritative_workload | implementation-operating-system | 9acd25a
CPI-000016 |  |  | task | TSK-000016 |  | TSK-000016 | task_effort |  |  | hours | authoritative_workload | implementation-operating-system | 9acd25a
CPI-000017 |  |  | task | TSK-000017 |  | TSK-000017 | task_effort |  |  | hours | authoritative_workload | implementation-operating-system | 9acd25a
CPI-000018 |  |  | task | TSK-000018 |  | TSK-000018 | task_effort |  |  | hours | authoritative_workload | implementation-operating-system | 9acd25a
CPI-000019 |  |  | task | TSK-000019 |  | TSK-000019 | task_effort |  |  | hours | authoritative_workload | implementation-operating-system | 9acd25a
CPI-000020 |  |  | task | TSK-000020 |  | TSK-000020 | task_effort |  |  | hours | authoritative_workload | implementation-operating-system | 9acd25a
CPI-000021 |  |  | task | TSK-000021 |  | TSK-000021 | task_effort |  |  | hours | authoritative_workload | implementation-operating-system | 9acd25a
CPI-000022 |  |  | task | TSK-000022 |  | TSK-000022 | task_effort |  |  | hours | authoritative_workload | implementation-operating-system | 9acd25a
CPI-000023 |  |  | task | TSK-000023 |  | TSK-000023 | task_effort |  |  | hours | authoritative_workload | implementation-operating-system | 9acd25a
CPI-000024 |  |  | task | TSK-000024 |  | TSK-000024 | task_effort |  |  | hours | authoritative_workload | implementation-operating-system | 9acd25a
CPI-000025 |  |  | task | TSK-000025 |  | TSK-000025 | task_effort |  |  | hours | authoritative_workload | implementation-operating-system | 9acd25a
CPI-000026 |  |  | task | TSK-000026 |  | TSK-000026 | task_effort |  |  | hours | authoritative_workload | implementation-operating-system | 9acd25a
CPI-000027 |  |  | task | TSK-000027 |  | TSK-000027 | task_effort |  |  | hours | authoritative_workload | implementation-operating-system | 9acd25a
CPI-000028 |  |  | task | TSK-000028 |  | TSK-000028 | task_effort |  |  | hours | authoritative_workload | implementation-operating-system | 9acd25a
CPI-000029 |  |  | task | TSK-000029 |  | TSK-000029 | task_effort |  |  | hours | authoritative_workload | implementation-operating-system | 9acd25a
CPI-000030 |  |  | task | TSK-000030 |  | TSK-000030 | task_effort |  |  | hours | authoritative_workload | implementation-operating-system | 9acd25a
CPI-000031 |  |  | request | REQ-000002 |  | TSK-000011 | request_handling |  |  | hours | excluded_to_prevent_double_count | implementation-operating-system | 9acd25a
CPI-000032 |  |  | request | REQ-000006 |  | TSK-000026 | request_handling |  |  | hours | excluded_to_prevent_double_count | implementation-operating-system | 9acd25a
CPI-000033 |  |  | handoff | HND-000002 |  | TSK-000026 | handoff_effort |  |  | hours | excluded_to_prevent_double_count | implementation-operating-system | 9acd25a
CPI-000034 |  |  | phase | PHS-000006 |  | PHS-000006 | phase_summary |  |  | hours | informational_only | implementation-operating-system | 9acd25a
CPI-000035 |  |  | phase | PHS-000015 |  | PHS-000015 | phase_summary |  |  | hours | informational_only | implementation-operating-system | 9acd25a

## Event Log
Event Log
Shared event contract (10 columns). Rows are imported or appended by a person; nothing is appended automatically. Check columns flag problems.
Event Log (shared event contract; entered or imported, never auto-appended)
event_id | event_type | occurred_at | actor_id | actor_type | subject_type | subject_id | payload | source_repo | schema_version | event_type_check | source_repo_check | actor_check | subject_check | payload_check | request_transition_check
EVT-000001 | project.created | 2026-09-08T14:00:00Z | PER-000001 | human | project | PRJ-000001 | {"status": "active", "profile_id": "PRF-000001", "target_launch_date": "2026-12-01"} | implementation-operating-system | 1.0.0
EVT-000002 | phase.entered | 2026-09-08T14:05:00Z | PER-000001 | human | phase | PHS-000001 | {"project_id": "PRJ-000001", "phase_key": "initiate"} | implementation-operating-system | 1.0.0
EVT-000003 | handoff.completed | 2026-09-08T14:10:00Z | PER-000001 | human | handoff | HND-000001 | {"project_id": "PRJ-000001", "from_role_id": "ROL-000008", "to_role_id": "ROL-000001"} | implementation-operating-system | 1.0.0
EVT-000004 | risk.logged | 2026-09-10T15:00:00Z | PER-000002 | human | risk | RSK-000002 | {"project_id": "PRJ-000002", "severity": "sev2", "risk_score": 12} | implementation-operating-system | 1.0.0
EVT-000005 | task.status_changed | 2026-09-10T17:00:00Z | PER-000001 | human | task | TSK-000001 | {"project_id": "PRJ-000001", "from_status": "in_progress", "to_status": "completed"} | implementation-operating-system | 1.0.0
EVT-000006 | milestone.achieved | 2026-09-10T20:30:00Z | PER-000001 | human | milestone | MLS-000001 | {"project_id": "PRJ-000001", "achieved_date": "2026-09-10"} | implementation-operating-system | 1.0.0
EVT-000007 | gate.assessed | 2026-09-11T13:30:00Z | PER-000003 | human | gate_assessment | GAT-000003 | {"project_id": "PRJ-000003", "phase_key": "validate", "outcome": "pass", "assessor_id": "PER-000003"} | implementation-operating-system | 1.0.0
EVT-000008 | phase.exited | 2026-09-11T14:00:00Z | PER-000003 | human | phase | PHS-000013 | {"project_id": "PRJ-000003", "phase_key": "validate", "gate_assessment_id": "GAT-000003"} | implementation-operating-system | 1.0.0
EVT-000009 | phase.entered | 2026-09-11T14:05:00Z | PER-000003 | human | phase | PHS-000014 | {"project_id": "PRJ-000003", "phase_key": "enable"} | implementation-operating-system | 1.0.0
EVT-000010 | gate.assessed | 2026-09-11T14:30:00Z | PER-000002 | human | gate_assessment | GAT-000002 | {"project_id": "PRJ-000002", "phase_key": "design", "outcome": "pass_with_conditions", "assessor_id": "PER-000002", "conditions": ["RSK-000002"]} | implementation-operating-system | 1.0.0
EVT-000011 | phase.exited | 2026-09-11T15:00:00Z | PER-000002 | human | phase | PHS-000005 | {"project_id": "PRJ-000002", "phase_key": "design", "gate_assessment_id": "GAT-000002"} | implementation-operating-system | 1.0.0
EVT-000012 | phase.entered | 2026-09-11T15:05:00Z | PER-000002 | human | phase | PHS-000006 | {"project_id": "PRJ-000002", "phase_key": "build"} | implementation-operating-system | 1.0.0
EVT-000013 | gate.assessed | 2026-09-15T15:45:00Z | PER-000001 | human | gate_assessment | GAT-000001 | {"project_id": "PRJ-000001", "phase_key": "initiate", "outcome": "pass", "assessor_id": "PER-000001"} | implementation-operating-system | 1.0.0
EVT-000014 | phase.exited | 2026-09-15T16:00:00Z | PER-000001 | human | phase | PHS-000001 | {"project_id": "PRJ-000001", "phase_key": "initiate", "gate_assessment_id": "GAT-000001"} | implementation-operating-system | 1.0.0
EVT-000015 | phase.entered | 2026-09-15T16:05:00Z | PER-000001 | human | phase | PHS-000002 | {"project_id": "PRJ-000001", "phase_key": "discover"} | implementation-operating-system | 1.0.0
EVT-000016 | request.submitted | 2026-09-15T17:00:00Z | PER-000002 | human | request | REQ-000002 | {"project_id": "PRJ-000002", "request_type": "access", "due_at": "2026-09-30T17:00:00Z"} | implementation-operating-system | 1.0.0
EVT-000017 | request.status_changed | 2026-09-15T19:00:00Z | PER-000002 | human | request | REQ-000002 | {"from_status": "submitted", "to_status": "triaged"} | implementation-operating-system | 1.0.0
EVT-000018 | request.status_changed | 2026-09-16T14:00:00Z | PER-000002 | human | request | REQ-000002 | {"from_status": "triaged", "to_status": "accepted"} | implementation-operating-system | 1.0.0
EVT-000019 | request.status_changed | 2026-09-16T15:00:00Z | PER-000002 | human | request | REQ-000002 | {"from_status": "accepted", "to_status": "in_progress"} | implementation-operating-system | 1.0.0
EVT-000020 | risk.logged | 2026-09-17T15:00:00Z | PER-000001 | human | risk | RSK-000001 | {"project_id": "PRJ-000001", "severity": "sev3", "risk_score": 6} | implementation-operating-system | 1.0.0
EVT-000021 | issue.logged | 2026-09-21T14:00:00Z | PER-000003 | human | issue | ISS-000004 | {"project_id": "PRJ-000003", "severity": "sev3"} | implementation-operating-system | 1.0.0
EVT-000022 | issue.resolved | 2026-09-23T16:00:00Z | PER-000003 | human | issue | ISS-000004 | {"project_id": "PRJ-000003", "resolution_summary": "Classes were moved to separate time slots."} | implementation-operating-system | 1.0.0
EVT-000023 | request.status_changed | 2026-09-24T15:00:00Z | PER-000002 | human | request | REQ-000002 | {"from_status": "in_progress", "to_status": "blocked", "reason": "Waiting for integration credentials from the customer."} | implementation-operating-system | 1.0.0
EVT-000024 | task.status_changed | 2026-09-24T15:30:00Z | PER-000002 | human | task | TSK-000011 | {"project_id": "PRJ-000002", "from_status": "in_progress", "to_status": "blocked"} | implementation-operating-system | 1.0.0
EVT-000025 | risk.status_changed | 2026-09-24T16:00:00Z | PER-000002 | human | risk | RSK-000002 | {"from_status": "open", "to_status": "mitigating", "risk_score": 12} | implementation-operating-system | 1.0.0
EVT-000026 | issue.logged | 2026-09-24T17:00:00Z | PER-000002 | human | issue | ISS-000002 | {"project_id": "PRJ-000002", "severity": "sev2"} | implementation-operating-system | 1.0.0
EVT-000027 | request.escalated | 2026-09-26T15:00:00Z | RUL-000003 | system | request | REQ-000002 | {"rule_id": "RUL-000003", "escalation_role_id": "ROL-000003", "severity": "sev2"} | implementation-operating-system | 1.0.0
EVT-000028 | milestone.achieved | 2026-09-29T19:30:00Z | PER-000003 | human | milestone | MLS-000011 | {"project_id": "PRJ-000003", "achieved_date": "2026-09-29"} | implementation-operating-system | 1.0.0
EVT-000029 | gate.assessed | 2026-09-30T14:30:00Z | PER-000003 | human | gate_assessment | GAT-000004 | {"project_id": "PRJ-000003", "phase_key": "enable", "outcome": "pass", "assessor_id": "PER-000003"} | implementation-operating-system | 1.0.0
EVT-000030 | phase.exited | 2026-09-30T15:00:00Z | PER-000003 | human | phase | PHS-000014 | {"project_id": "PRJ-000003", "phase_key": "enable", "gate_assessment_id": "GAT-000004"} | implementation-operating-system | 1.0.0
EVT-000031 | phase.entered | 2026-09-30T15:05:00Z | PER-000003 | human | phase | PHS-000015 | {"project_id": "PRJ-000003", "phase_key": "launch"} | implementation-operating-system | 1.0.0
EVT-000032 | readiness.scored | 2026-10-01T15:00:00Z | RUL-000301 | system | readiness_scorecard | RDS-000001 | {"project_id": "PRJ-000001", "readiness_score": 16.25, "category_scores": {"people": 7.5, "process": 3.75, "technology": 0.0, "data": 5.0, "training": 0.0, "support": 0.0}} | implementation-operating-system | 1.0.0
EVT-000033 | readiness.scored | 2026-10-01T16:00:00Z | RUL-000301 | system | readiness_scorecard | RDS-000002 | {"project_id": "PRJ-000002", "readiness_score": 37.5, "category_scores": {"people": 11.25, "process": 11.25, "technology": 10.0, "data": 5.0, "training": 0.0, "support": 0.0}} | implementation-operating-system | 1.0.0
EVT-000034 | readiness.scored | 2026-10-02T15:00:00Z | RUL-000301 | system | readiness_scorecard | RDS-000003 | {"project_id": "PRJ-000003", "readiness_score": 91.25, "category_scores": {"people": 15.0, "process": 15.0, "technology": 25.0, "data": 15.0, "training": 11.25, "support": 10.0}} | implementation-operating-system | 1.0.0
EVT-000035 | handoff.completed | 2026-10-02T17:00:00Z | PER-000005 | human | handoff | HND-000002 | {"project_id": "PRJ-000003", "from_role_id": "ROL-000004", "to_role_id": "ROL-000006"} | implementation-operating-system | 1.0.0
EVT-000036 | request.status_changed | 2026-10-02T17:05:00Z | PER-000005 | human | request | REQ-000006 | {"from_status": "ready_for_handoff", "to_status": "handed_off"} | implementation-operating-system | 1.0.0
EVT-000037 | milestone.missed | 2026-10-03T09:00:00Z | PER-000002 | human | milestone | MLS-000005 | {"project_id": "PRJ-000002", "due_date": "2026-10-02", "reason": "Integration credentials have not been provided."} | implementation-operating-system | 1.0.0
EVT-000038 | request.submitted | 2026-10-05T14:00:00Z | PER-000003 | human | request | REQ-000008 | {"project_id": "PRJ-000003", "request_type": "information", "due_at": "2026-10-09T17:00:00Z"} | implementation-operating-system | 1.0.0

## KPI Summary
KPI Summary
Operational view traced to R1 records. Not a metric authority, not a forecast, and not a performance measure.
KPI summary (operational view; not a metric authority) | [5 empty] | Projects by current phase |  |  | Requests by status |  |  | Readiness by project
kpi_key | label | value | grain | source_table | authority_classification | position | phase_key | project_count | position | request_status | request_count | position | project_id | readiness_score | evidence_warning
project_count | Projects |  | workbook | tblProjects | summarizes_r1_records | 1 |  |  | 1 |  |  | 1
active_project_count | Active projects |  | workbook | tblProjects | summarizes_r1_records | 2 |  |  | 2 |  |  | 2
open_task_count | Open tasks (not completed or cancelled) |  | workbook | tblTasks | summarizes_r1_records | 3 |  |  | 3 |  |  | 3
blocked_task_count | Blocked tasks |  | workbook | tblTasks | summarizes_r1_records | 4 |  |  | 4 |  |  | 4
overdue_task_count | Overdue tasks as of calculation_as_of_at |  | workbook | tblTasks | r3_workbook_validation | 5 |  |  | 5 |  |  | 5
open_risk_count | Open risks (open or mitigating) |  | workbook | tblRisks | summarizes_r1_records | 6 |  |  | 6 |  |  | 6
open_issue_count | Open issues (open or in progress) |  | workbook | tblIssues | summarizes_r1_records | 7 |  |  | 7 |  |  | 7
request_count | Requests |  | workbook | tblRequests | summarizes_r1_records | 8 |  |  | 8 |  |  | 8
escalation_due_request_count | Requests whose escalation time has passed |  | workbook | tblRequests | r3_workbook_validation | 9 |  |  | 9 |  |  | 9
readiness_scorecard_count | Readiness scorecards |  | workbook | tblReadinessSummary | summarizes_r1_records | 10 | [5 empty] | 10
incomplete_readiness_evidence_count | Scorecards with incomplete required evidence |  | workbook | tblReadinessSummary | summarizes_r1_records
event_log_row_count | Event Log rows |  | workbook | tblEventLog | summarizes_r1_records
event_log_problem_count | Event Log rows failing a check |  | workbook | tblEventLog | r3_workbook_validation
missing_event_evidence_count | Material changes inside the window with no Event Log row |  | workbook | all record tables | r3_workbook_validation
reference_problem_count | Records with an unresolved reference |  | workbook | all record tables | r3_workbook_validation